## Backlog
ID	Importance	Story	Notes	Points	Andrew	Charles	Daniel
1	999	- Login (Session / cookie )	User part	15	5	5	5
2	555	- Add to basket	User part	11	4	4	3
3	550	- remove from basket	User part	11	4	4	3
4	400	- Order from basket	User part	9	3	2	4
5	999	- Sign up	User part	8	3	2	3
6	400	- Adding new product	Admin part	7	3	2	2
7	400	- Remove product	Admin part	7	3	2	2
8	300	- Listing product by criteria	User part	6	1	3	2
9	300	- Change product prices	Admin part	6	2	2	2
10	300	- Add comments	User part	6	1	3	2
11	500	- admin comments	Admin part	4	2	1	1
12	100	- List Users	User part / Admin part	3	1	1	1

## Timetabel
Time Period:	From 10 of january to the 24 of january

Story ID	Story/task	10	11	12	13	14	15	16	17	18	19	20	21	22	23	Task taker/Person	Comments
1	- Login (Session / cookie )	15					Charles
2	- Add to basket	7					7	6				Daniel
3	- remove from basket	7					7	6				Daniel
6	- Adding new product	7					Andrew
7	- Remove product	7					Andrew