## Backlog
ID	Importance	Story	Notes	Points	Andrew	Charles	Daniel
1	999	- Login (Session / cookie )	User part	15	5	5	5
2	555	- Add to basket	User part	11	4	4	3
3	550	- remove from basket	User part	11	4	4	3
4	400	- Order from basket	User part	9	3	2	4
5	999	- Sign up	User part	8	3	2	3
6	400	- Adding new product	Admin part	7	3	2	2
7	400	- Remove product	Admin part	7	3	2	2
8	300	- Listing product by criteria	User part	6	1	3	2
9	300	- Change product prices	Admin part	6	2	2	2
10	300	- Add comments	User part	6	1	3	2
11	500	- admin comments	Admin part	4	2	1	1
12	100	- List Users	User part / Admin part	3	1	1	1

		Sorted by priority

## Timetabel
Time Period:	From 10 of january to the 24 of january
Sprint 1	Story/task
Story ID			10	11	12	13	14	15	16	17	18	19	20	21	22	23	Task taker/Person	Comments
1	- Login (Session / cookie )	15	15	15	15	15	7	7	7	2	2	0	0	0	0	0	Charles
2	- Add to basket	7	7	7	7	7	2	2	2	2	1	1	0	5	5	5	Daniel	Problems with the many-to-many relationship in the database made us choose a solution that when integrated to the master branch didn't work as expected.
3	- remove from basket	7	7	7	7	7	2	3	2	2	1	1	0	5	5	5	Daniel
6	Adding new product	7	7	7	7	7	2	2	2	3	3	3	3	3	3	3	Andrew
7	- Remove product	7	7	7	7	7	7	7	7	7	7	7	7	5	5	5	Andrew
	Total time	43	43	43	43	43	20	21	20	16	14	12	10	18	18	18

Sprint 2
Story ID	Story/task		24	25	26	27	28	29	30	31	1	2	3	4	5	6	Task taker/Person	Comments
1	Creating View	15					Andrew
2	Order from basket	7					Daniel
3	Treatment of the order	7					Daniel
6	Reorgainisation of user	7					Charles
7	Development of user data storage	15					Charles
	Total time	51
January
Estimated time left (hours)
January
Estimated time left (hours)