## Product Backlog
Description
Add and remove products to a database
Register as user
User can browse products
User can choose a product and put it in a basket
User can log in and log out
User can edit account details
Add and remove employees
Employees can search for users
Employees can edit products
Administrator can add and remove employees
Administrator can search for employees
User can see purchase history
User can check out basket

## Sprint Backlog
ID	Completed	Story	Notes					ID starting number
101	X	Log in (Session / cookie )	User					User: 1
102	X	Add to basket	User					Admin: 2
103	X	Remove from basket	User					Views: 3
104	X	Order from basket	User					Other: 4
105	X	Sign up	User					Super admin: 5
106	X	Listing product by criteria	User
107	s4	Add comments	User
201	X	Adding new product	Admin
210	s3	List Users	Admin
202	s3	Remove product	Admin
203	s4	Change product prices	Admin
204		Admin comments	Admin
205	X	Create category	Admin
206	X	Delete category	Admin
207	s4	Storing user data	Admin
208	s4	Treating order	Admin
209	s4	Search for employee	Admin
301	s3	Create user	View
302	s3	List Users	View
303	X	List Products	View
304	s3	List Users	View
305	s4	View Basket/cart	View
306	s4	Front Page	View
307	s4	Login	View
308	s4	Error page	View
309	s4	Add/remove category	View
401	X	Email validation	Other
402	s4	Unit test	Other
403	X	Mock object?	Other
404	X	Reorganize the users	wtf is this?
405	X	Webpage filter	Other
501	s3	Add employee	Super admin
502	s3	Remove employee	Super admin
108	s5	Log out	user and admin
310	s5	Admin control panel	view
311	s5	Super admin control panel	view

## Timetabel
	2014-01-10
	Sprint 1
ID	Story/task		10	11	12	13	14	15	16	17	18	19	20	21	22	23	Task taker	Comments
1.1	Login (Session / cookie )	15	15	15	15	15	7	7	7	2	2	0	0	0	0	0	Charles
1.2	Add to basket	7	7	7	7	7	2	2	2	2	1	1	0	5	5	5	Daniel	Problems with the many-to-many relationship in the database made us choose a solution that when integrated to the master branch didn't work as expected.
1.3	Remove from basket	7	7	7	7	7	2	3	2	2	1	1	0	5	5	5	Daniel
2.1	Adding new product	7	7	7	7	7	2	2	2	3	3	3	3	3	3	3	Andrew
2.2	Remove product	7	7	7	7	7	7	7	7	7	7	7	7	5	5	5	Andrew
	Total time	43	43	43	43	43	20	21	20	16	14	12	10	18	18	18

	Sprint 2
ID	Story/task		24	25	26	27	28	29	30	31	1	2	3	4	5	6	Task taker	Comments
1.4	Order from basket	12	12	12	8	0	0	0	0	0	0	0	0	Charles
1.5	Sign up	12	12	12	12	12	8	5	0	0	0	0	0	0	0	0	Charles
1.6	Delete category	5	5	5	5	5	5	5	3	3	0	0	0	0	0	0	Daniel
2.7	Storing user data	5	5	5	5	5	5	5	2	3	0	0	0	0	0	0	Andrew
2.5	Create category	5	5	5	5	5	5	5	5	5	2	0	0	0	Daniel
1.2	Add to basket	5	2	0	0	0	0	0	0	0	0	0	0	0	0	0	Daniel
1.3	Remove from basket	3	0	0	0	0	0	0	0	0	0	0	0	0	0	0	Daniel
2.1	Adding new product	3	0	0	0	0	0	0	0	0	0	0	0	0	0	0	Andrew
2.2	Remove product	5	5	2	0	0	0	0	0	0	0	0	0	0	0	0	Andrew
	Total time	55	46	41	35	27	23	20	10	11	5	5	2	0	0	0

	Sprint 3
ID	Story/task		7	8	9	10	11	12	13	14	15	16	17	18	19	20	Task taker	Comments
1.4	Order from basket	15	15	15	15	15	10	8	8	8	15	7	0	0	0	0	Charles	User : A few bug caused by the @NotNull anotation put by Netbeans
1.8	List Users	5	0	0	0	0	0	0	0	0	Charles	User : Quick task.
2.1	Adding new product	5	5	5	5	5	2	0	0	0	0	0	0	0	0
2.2	List Users	5	5	5	5	5	5	0	0	0	0	0	0	0	0
2.5	Create category	10	10	10	10	10	5	1	1	1	1	0	0	0	0	0
3.1	Create user	5	5	5	5	5	3	3	3	3	3	0	0	0	0	0	Andrew	View
3.2	List Users	5	5	5	5	5	5	3	3	3	3	0	0	0	0	0	Andrew	View
3.3	List Products	5	5	5	5	5	5	5	5	5	1	0	0	Andrew	View
3.4	List Users	5	5	5	5	5	5	5	5	5	2	0	0	0	Andrew	View
5.1	Add employee	5	5	5	5	5	5	5	5	5
5.2	Remove employee	5	5	5	5	5	5	5	5	5
	Total time	70	65	65	65	65	50	35	35	35	42	27	17	11	10	10

	Sprint 4
ID	Story/task		21	22	23	24	25	26	27	28	1	2	3	4	5	6	Task taker	Comments
1.7	Add comments	10	10	10	5	0	0	0	0	0	0	0	0
2.3	Change product prices	3	3	3	0	0	0	0	0	0	0	0
2.7	Storing user data	5	5	5	5	2	0	0	0	0	0	0	0	0
2.8	Treating order	7	7	7	7	7	7	7	7	5	0	0	0	0	0	0
2.9	Search for employee	3	3	3	3	3	3	3	3	3
3.5	View Basket/cart	3	3	3	0	0	0	0	0	0	0	0
3.6	Front Page	5	5	5	5	2	0	0	0	0	0	0	0	0
3.7	Login	4	4	4	4	0	0	0	0	0	0	0	0
3.8	Error page	5	5	5	5	5	5	5	5	5	0	0	0	0	0
3.9	Add/remove category	3	3	3	3	3	3	3	3	0	0	0	0	0	0	0
4.2	Unit test	7	7	7	7	7	7	7	7	7
4.3	Mock object?	7	7	7	7	7	7	7	7	7	#NAME?	#NAME?	#NAME?
5.1	Add employee	5	5	5	5	5	5	5	5	5
5.2	Remove employee	5	5	5	5	5	5	5	5	5
	Total time	72	59	59	56	46	42	42	42	37	32	27	27	#NAME?	#NAME?	#NAME?

	Sprint 5
ID	Story/task		7	8	9	10	11	12	13	14	15	16	17	18	19	20	Task taker	Comments
January
Estimated time left (hours)
January
Estimated time left (hours)

## Charles stuff
Change the database : remove the unused Basket field, recreate everything with Mysql_workbench with better foreign key between table	3h30
Creation of basic view (no css, really basic, to wait for the real view to be finished):
category.jsp : print all the category and the product for the category selected
user.jspf : user interface (cart/name)
login.jsp : form for login
Creation of the classes ShoppingCart and ShoppingCartItem to implement the model for the Cart	2h
Transform all the logic through the use of Session Bean : auto-creation of the entityFacade with some new request (User.findByLogin, etc ...)	20min
Implementation of a "slug" interface for category : now to ask for all the products for one category you have to call for /category/{category}	1h
Creation of a session bean singleton : CategoryPool to stock all the category of the application	40min
Creation of the filter for the management of checkout/purchase : since the users have to been authenticated, the filter check for these url if there is a user	1hour
Creation of a new Constraint : EmailValid, taken from a website, and implement it on internet	40min